## Feuil1
Distributed Programming Project
Hugo Vouillamoz & Benjamin Morel
Total estimate of time spent on the projet : ~20-25 hours/person
Problems encountered :
- Initially I didn't really know how to manage the management of multiple clients on the same server. I had to find out more on the internet.
- Concerning the swing part for GUI and also for the JSON Serialisation, I went back to see the course of the previous semester.
- To run a .jar on linux, I had to adapt the code of the server but it was very interesting.
- For the other parts, I didn't have too many problems, the exercises done in class were enough to solve them, I just had to make reseraches by myself.
- The collaboration with Hugo went very well, we worked together and I am very happy of the final result.
| November |  |  |  |  | December |  |  |  | January
Tasks | 2021-11-02 | 2021-11-09 | 2021-11-16 | 2021-11-23 | 2021-11-30 | 2021-12-07 | 2021-12-14 | 2021-12-21 | 2021-12-28 | 2022-01-04 | 2022-01-13
Creation of the gitlab | bar: 2021-11-02
Creation of .gitignore + pom.xml for maven project | bar: 2021-11-02
Adding base project, with multi thread on server | bar: 2021-11-09 to 2021-11-16
Adding classes for client connection | bar: 2021-11-16 to 2021-11-30
GUI for song page | bar: 2021-11-23 to 2021-11-30
Adding volume changes, images | bar: 2021-11-30 to 2021-12-07
JSON Serialisation | bar: 2021-11-30 to 2021-12-07; 2021-12-28 to 2022-01-04
Run .jar on linux and code update for server part | bar: 2021-11-30 to 2021-12-07; 2021-12-28 to 2022-01-04
Adding logs | bar: 2021-12-28 to 2022-01-04
Adding comments for every method | bar: 2021-12-28 to 2022-01-04
Final check + preparation for the presentation | bar: 2022-01-04
Final deliverable